## Data generator (hidden)
Project History: The following is a record of proxies used in past projects.
| Identifier | Total Loc | Methods | Type |  | loc/meth | ave | std | type
| Proxy1 | 116 | 5 | Calculation |  | 23.2 | 27.645 | 15.4851 | LOG
| Proxy2 | 76 | 3 | Calculation |  | 25.3333
| Proxy3 | 124 | 6 | Calculation |  | 20.6667
| Proxy4 | 60 | 4 | Calculation |  | 15
| Proxy5 | 70 | 3 | Calculation |  | 23.3333
| Proxy6 | 124 | 2 | Calculation |  | 62
| Proxy7 | 122 | 3 | Calculation |  | 40.6667
| Proxy8 | 49 | 6 | Calculation |  | 8.1667
| Proxy9 | 79 | 4 | Calculation |  | 19.75
| Proxy10 | 115 | 3 | Calculation |  | 38.3333
| Proxy11 | 105 | 5 | Data |  | 21 | 21.3635 | 17.8171 | LOG
| Proxy12 | 86 | 6 | Data |  | 14.3333
| Proxy13 | 79 | 8 | Data |  | 9.875
| Proxy14 | 69 | 5 | Data |  | 13.8
| Proxy15 | 86 | 6 | Data |  | 14.3333
| Proxy16 | 48 | 3 | Data |  | 16
| Proxy17 | 79 | 1 | Data |  | 79
| Proxy18 | 101 | 6 | Data |  | 16.8333
| Proxy19 | 124 | 5 | Data |  | 24.8
| Proxy20 | 69 | 6 | Data |  | 11.5
| Proxy21 | 89 | 4 | Data |  | 22.25
| Proxy22 | 128 | 8 | Data |  | 16
| Proxy23 | 90 | 5 | Data |  | 18
| Proxy24 | 156 | 1 | I/O |  | 156 | 50.0786 | 48.3919 | LOG
| Proxy25 | 147 | 6 | I/O |  | 24.5
| Proxy26 | 61 | 4 | I/O |  | 15.25
| Proxy27 | 102 | 2 | I/O |  | 51
| Proxy28 | 127 | 5 | I/O |  | 25.4
| Proxy29 | 105 | 4 | I/O |  | 26.25
| Proxy30 | 78 | 5 | I/O |  | 15.6
| Proxy31 | 86 | 7 | I/O |  | 12.2857
| Proxy32 | 121 | 2 | I/O |  | 60.5
| Proxy33 | 114 | 1 | I/O |  | 114
Project History: The following is a record of actual/estimated performance on past projects. Note: times are in minutes.
| Identifier | Est. LOC | Actual LOC | Est. Duration | Actual Duration |  | ExA
| Project1 | 353 | 249 | 900 | 600 |  | r | 0.5641
| Project2 | 236 | 148 | 600 | 360 |  | r2 | 0.31821
| Project3 | 456 | 278 | 1140 | 660 |  | sig | 0.013364
| Project4 | 308 | 453 | 780 | 1200
| Project5 | 331 | 324 | 780 | 660 |  | ExT
| Project6 | 295 | 253 | 720 | 600 |  | r | 0.58518
| Project7 | 333 | 276 | 900 | 660 |  | r2 | 0.34243
| Project8 | 351 | 393 | 900 | 1140 |  | sig | 0.012113
| Project9 | 419 | 439 | 1080 | 960
| Project10 | 521 | 432 | 1380 | 1140 |  | AxT
| Project11 | 386 | 365 | 960 | 1020 |  | r | 0.90517
| Project12 | 369 | 237 | 900 | 660 |  | r2 | 0.81934
| Project13 | 338 | 277 | 840 | 720 |  | sig | 1.0596e-06
| Project14 | 150 | 180 | 420 | 480
| Project15 | 239 | 320 | 600 | 780
| Project16 | 296 | 312 | 720 | 780
| Project17 | 474 | 322 | 1140 | 1020
| Project18 | 397 | 424 | 960 | 900
| Project19 | 273 | 186 | 660 | 540
| Project20 | 330 | 366 | 900 | 780
Project History: The following describes the to-date percentages for development time and defects.
|  | Phase | Time in Phase To Date % | Defects Injected To Date % | Defects Removed To Date %
|  | Planning | 21% | 0% | 0%
|  | Design | 18% | 2% | 4%
|  | Code | 1% | 73% | 1%
|  | Compile | 4% | 5% | 27%
|  | Test | 55% | 20% | 68%
|  | Postmortem | 1% | 0% | 0%
|  | Total | 100% | 100% | 100%
New Development: The following information pertains to new development. Specifically, it notes that the new development will build from pre-existing code, with some deletions and modifications. New proxies (whether additions to the base code or totally new functionality) are also specified.
Base Program LOC
|  | Base Size (B) |  | 393
|  | LOC Deleted (D) |  | 15
|  | LOC Modified (M) |  | 15
Object LOC (BA)
|  | Base Additions | Type | Methods | Relative Size
|  | BA1 | Data | 10 | S
|  | BA2 | Data | 9 | S
New Objects (NO)
|  | New Objects | Type | Methods | Relative Size
|  | NO0 | Calculation | 8 | VL
|  | NO1 | IO | 4 | S
|  | NO2 | IO | 1 | S
|  | NO3 | Data | 3 | VL
|  | NO4 | Calculation | 5 | L
|  | NO5 | Calculation | 7 | VL
Types
1 | Calculation
2 | IO
3 | Data
1 | VS
2 | S
3 | M
4 | L
5 | VL
proxies | 0 | LOG | LOG | LOG
history | 0 | 0.31821 | 0.013364 | 0.34243 | 0.012113 | 0.81934 | 1.0596e-06

## Solution (hidden)
Solution
Name:
Language:
WebCT login:
Changes have been made to 1.xls since the last homework submission:
Assignment: |  | 5
6700 Due: |  | 2020-04-11 | 11:55pm
6706 Due: |  | 0 | 0
Name of file: |  | 5.xls
Table of Contents
go to | Instructor Assessment:
go to | Project Plan Summary
go to | Time Log
go to | Defect Log
go to | Size Estimation
go to | Task Plan
go to | Schedule
go to | Operational Scenario
go to | Functional Specification
go to | Test Report
go to | Lessons Learned
go to | LOC Counting Std
go to | LOC Coding Std
go to | Size Estimation
go to | Conceptual Design
go to | Review Checklists
go to | Task Plan
go to | Schedule
go to | Operational Spec
go to | Functional Spec
go to | Logic Spec
go to | State spec
go to | Source Code
Instructor Assessment
Aspect | Criteria | Possible Score | Score | Comment
Proxy categorization
| Correct calculations | 2
| Appropriate sizing | 2
Size estimate
| E derived from db | 2
| Correct regression | 2
| Correct range | 2
Duration
| Correct productivity | 2
| Appropriate duration | 2
| Correct range | 2
Time in Phase
| Correct distribution | 2
Supporting Calcs
| Traceable if in error (max of -2) | 0
Base |  | 0
0
| Total | 18 | 0
Estimates on New Development: Please provide answers to the questions below. If a result is not calculable, please fill the box with a "NA" and defend your answer in the supporting calculations section. Each cell should contain a number, "NA", or a val
Parameters
normal
log-normal
not applicable
LOCE x Time
LOCA x Time
Productivity
not applicable
Object Category Sizes (in LOC/Method)
| Category | VS midpoint | S midpoint | M midpoint | L midpoint | VL midpoint | Method Used
Calculation
Data
IO
Logic
Set-up
Text
Size Estimate
| Base Additions (BA) | [6 empty] | LOC
| New Object LOC (NO) | [6 empty] | LOC
| Estimated Object LOC (E) |  |  | E=BA+NO+M |  |  |  | LOC
| Regression Parm |  |  | B0
| Regression Parm |  |  | B1
| Estimated New and Changed LOC (N) |  |  | N=B0+B1*E |  |  |  | LOC
| Estimated Total LOC (T) |  |  | T=N+B-D-M |  |  |  | LOC
| 70% Prediction Range (Rangesize) |  |  | Rangesize |  |  |  | LOC
| Upper Prediction Interval (UPIsize) |  |  | UPIsize=N+Rangesize |  |  |  | LOC
| Lower Prediction Interval (LPIsize) |  |  | LPIsize=N-Rangesize |  |  |  | LOC
Duration Estimate
| Productivity |  |  | Planned LOC/hour |  |  |  | LOC/hour
| Estimated Project Duration (minutes) |  |  | method= |  |  |  | Minutes
| 70% Prediction Range (Rangeduration) |  |  | Rangeduration |  |  |  | Minutes
| Upper Prediction Interval (UPIduration) |  |  | UPIduration=Time+Rangeduration |  |  |  | Minutes
| Lower Prediction Interval (LPIduration) |  |  | LPIduration=Time-Rangeduration |  |  |  | Minutes
Time in Phase Estimate (minutes)
| Planning |  | Minutes
| Design |  | Minutes
| Code |  | Minutes
| Compile |  | Minutes
| Test |  | Minutes
| Postmortem |  | Minutes
| Total |  | Minutes

## Description
CS 312 -- Software Engineering
Assignment: | 5
Due date: | 2020-04-11 | 11:55pm
Name of this file: | 5.xls
Objective: | to gain experience with estimating size and duration.
Assignment: | The worksheets in this assignment provide you with a hypothetical historical development database as well as with a forecast of standard components for a hypothetical project. Please use this information to determine the size and duration of the project.
Notes: | - This homework assignment is be accomplished individually
Deliverables: | - This spreadsheet with "Assignment" completed.
- Python code to read the historical data and calculate values necessary to complete the Xcel file.
- (Optional) Explanatory calculations on worksheets "Calc-1", "Calc-2", etc.
- When complete, upload the spreadsheet to OneDrive.

## Process
Process Script
Entry |  | - this spreadsheet
Tasks |  | 1. Develop and record a database of proxy sizes for each proxy type.
Sort the proxies into types
For each type do:
calculate the average and standard deviation of the number of lines of code per method
if the mean > 2*std, then
VS=mean-2*std, S=mean-std, M=mean, L=mean+std, VL=mean+2*std
else
calculate the average and standard deviation of the log of the number of lines of code per method
VS=antilog(mean-2*std), S=antilog(mean-std), M=antilog(mean), etc.
end if
end do
ensure all proxy sizes are calculated using a consistent method
2. Size the proxies
Designate the size of each historical proxy as VS, S, M, L VL
For each Base Addition and New Object do:
designate the relative size of the proxy as the size of the proxy it is most similar to (see "similar to" column)
designate the type of the proxy as the type of the proxy it is most similar to (see "similar to" column)
determine the proxy size by multiplying the number of methods by the size in the size matrix
end do
3. Estimate the size
E=BA+NO+M
If LOCe is significantly correlated with LOCa
calculate B0 and B1 as you did in previous assignment
else
B0=0 and B1=1
end if
N=B1*E+B0
If LOCe is significantly correlated with LOCa then
calculate range according to table A29 (page 550)
calculate UPI and LPI
if LPI < 1 then
LPI = "NA"
end if
else
range = "NA", LPI="NA", UPI="NA"
end if
4. Estimate and record the duration of the new project.
Calculate productivity as sum(LOCa of all projects)/sum(actual duration of all projects)
If LOCe is significantly correlated with actual duration then
record duration method as "LOCe x Time"
duration = N*B1+B0, where B1 and B0 are derived from LOCe and actual duration
calculate range
else If LOCa is significantly correlated with actual duration then
record duration method as "LOCa x Time"
duration = N*B1+B0, where B1 and B0 are derived from LOCa and actual duration
calculate range
else
record duration method as "Productivity"
duration = N/productivity, range = NA
end if
5. Distribute and record time among project phases
Exit |  | - complete "Assignment" worksheet
- (optional) intermediate calculations
Quality checks
General
Are all regions highlighted in yellow complete? (Either with a value, or NA if the cell is not applicable. No units of measure.)
Are supporting calculations understandable?
Object Category Sizes
Are proxy buckets sized by either a normal or log-normal distribution?
Is preference given to sizing proxy "buckets" along a normal distribution?
Are proxy types sized consistently?
Proxy Sizing
Has each Base Addition and New Object been given a type and relative size?
Are base additions and new objects sized according to the size matrix?
Size Estimate
Is the adjusted estimate of size calculated according to the relationship that exists between LOCe and LOCa?
Are the regression parameters valid? Are they correct?
Is the range calculation valid? It is correct?
Does the Lower Prediction Interval (LPI) represent a valid concept?
Duration Estimate
Is the method used for duration estimation appropriate given the historical data?
Is duration based on the size of new code?
Is the range calculation valid? It is correct?
Useful Excel Functions
tdist
|  | parms: | t, degrees of freedom, number of tails (1 or 2)
|  | returns: | area under tails
|  | example: | "=TDIST(1.325,20,2)" yields | 0.20011
|  | note: | tdist returns 1-p(alpha) when tails=1 and
1-p(alpha/2) when tails = 2.
| tinv | parms: | probability, degrees of freedom
|  | returns: | the value of t such that the area under the T-curve from [-t,t] is the probability
|  | example: | "=TINV(0.200111,20)" yields | 1.325
| correl | parms: | x's, y's
|  | returns: | correlation coefficient
|  | example: | given the data at right, | X | Y
|  |  | "=CORREL(F83:F88,G83:G88)" | 1 | 2
|  |  | yields | 2 | 4
|  |  | 0.98372 | 4 | 8
|  |  |  | 5 | 10
|  |  |  | 6 | 12
|  |  |  | 7 | 17
| slope | parms: | y's, x's
|  | returns: | regression value B1
|  | example: | given the data above, "=SLOPE(G83:G88,F83:F88)" yields |  |  | 2.3168
| intercept | parms: | y's, x's
|  | returns: | regression value B0
|  | example: | given the data above, "=INTERCEPT(G83:G88,F83:F88)" yields |  |  | -0.81988
| average | parms: | values
|  | returns: | average of the values
|  | example: | the average of the x's above is "=AVERAGE(F83:F88)", or |  |  | 4.1667
| stdev | parms: | values
|  | returns: | standard deviation of the values
|  | example: | the std of the x's above is "=STDEV(F83:F88)", or |  |  | 2.3166
| sum | parms: | values
|  | returns: | sum of the values
|  | example: | the sum of the x's above is "=SUM(F83:F88)", which yields |  |  | 25
| ^ | parms: | value, power
|  | returns: | value**power
|  | example: | 5 squared is 5^2

## Data
Project History: The following is a record of proxies used in past projects.
| Identifier | Total Loc | Methods | Type
| Proxy01 | 93 | 5 | Calculation
| Proxy02 | 112 | 1 | Calculation
| Proxy03 | 79 | 1 | Calculation
| Proxy04 | 126 | 6 | Calculation
| Proxy05 | 68 | 1 | Calculation
| Proxy06 | 128 | 6 | Calculation
| Proxy07 | 141 | 3 | Calculation
| Proxy08 | 142 | 1 | Calculation
| Proxy09 | 58 | 6 | Calculation
| Proxy10 | 79 | 3 | Calculation
| Proxy11 | 95 | 5 | Data
| Proxy12 | 127 | 4 | Data
| Proxy13 | 90 | 6 | Data
| Proxy14 | 122 | 5 | Data
| Proxy15 | 97 | 5 | Data
| Proxy16 | 131 | 5 | Data
| Proxy17 | 118 | 3 | Data
| Proxy18 | 122 | 5 | Data
| Proxy19 | 42 | 4 | Data
| Proxy20 | 107 | 4 | Data
| Proxy21 | 94 | 6 | Data
| Proxy22 | 131 | 6 | Data
| Proxy23 | 89 | 5 | Data
| Proxy24 | 125 | 5 | I/O
| Proxy25 | 106 | 7 | I/O
| Proxy26 | 92 | 10 | I/O
| Proxy27 | 101 | 8 | I/O
| Proxy28 | 38 | 5 | I/O
| Proxy29 | 104 | 3 | I/O
| Proxy30 | 26 | 5 | I/O
| Proxy31 | 75 | 2 | I/O
| Proxy32 | 114 | 2 | I/O
| Proxy33 | 90 | 6 | I/O
Project History: The following is a record of actual/estimated performance on past projects. Note: times are in minutes.
| Identifier | Est. LOC (LOCe) | Actual LOC (LOCa) | Est. Duration (De) | Actual Duration (Da)
| Project1 | 124 | 98 | 360 | 300
| Project2 | 360 | 284 | 900 | 720
| Project3 | 229 | 292 | 540 | 720
| Project4 | 321 | 286 | 840 | 780
| Project5 | 279 | 350 | 720 | 900
| Project6 | 352 | 464 | 780 | 1380
| Project7 | 297 | 381 | 780 | 1020
| Project8 | 263 | 369 | 660 | 960
| Project9 | 357 | 365 | 900 | 900
| Project10 | 311 | 284 | 780 | 720
| Project11 | 341 | 277 | 840 | 600
| Project12 | 153 | 212 | 420 | 480
| Project13 | 390 | 319 | 1020 | 720
| Project14 | 260 | 218 | 660 | 540
| Project15 | 215 | 238 | 540 | 600
| Project16 | 468 | 312 | 1200 | 660
| Project17 | 528 | 676 | 1260 | 1620
| Project18 | 232 | 266 | 600 | 840
| Project19 | 304 | 225 | 780 | 600
| Project20 | 459 | 395 | 1080 | 1080
Project History: The following describes the to-date percentages for development time and defects.
| Phase | Time in Phase To Date % | Defects Injected To Date % | Defects Removed To Date %
| Planning | 14% | 0% | 0%
| Design | 21% | 1% | 2%
| Code | 3% | 77% | 7%
| Compile | 3% | 1% | 25%
| Test | 57% | 21% | 66%
| Postmortem | 2% | 0% | 0%
| Total | 100% | 100% | 100%
New Development: The following information pertains to new development. Specifically, it notes that the new development will build from pre-existing code, with some deletions and modifications. New proxies (whether additions to the base code or totally new functionality) are also specified.
Base Program LOC
|  | Base Size (B) | 369
|  | LOC Deleted (D) | 14
|  | LOC Modified (M) | 14
Object LOC (BA)
|  | Base Additions | Methods | Similar to
|  | BA1 | 6 | Proxy08
|  | BA2 | 2 | Proxy27
New Objects (NO)
|  | New Objects | Methods | Similar to
|  | NO0 | 5 | Proxy17
|  | NO1 | 2 | Proxy14
|  | NO2 | 4 | Proxy20
|  | NO3 | 3 | Proxy18
|  | NO4 | 5 | Proxy01
|  | NO5 | 7 | Proxy05

## Assignment
Process Information
Name: |  | D.S.Raghuveer
Language:
Roll No: |  | 18XJ1A0518
Changes have been made to 1.xls since the last homework submission:
Assignment: |  | 5
Due Date: |  | 2020-04-11 | 11:55pm
Name of file: |  | 5.xls
Table of Contents
go to | Instructor Assessment:
go to | Project Plan Summary
go to | Time Log
go to | Defect Log
go to | Size Estimation
go to | Task Plan
go to | Schedule
go to | Operational Scenario
go to | Functional Specification
go to | Test Report
go to | Lessons Learned
go to | LOC Counting Std
go to | LOC Coding Std
go to | Size Estimation
go to | Conceptual Design
go to | Review Checklists
go to | Task Plan
go to | Schedule
go to | Operational Spec
go to | Functional Spec
go to | Logic Spec
go to | State spec
go to | Source Code
Instructor Assessment
Aspect | Criteria | Possible Score | Score | Comment
Proxy categorization
| Correct calculations | 2
| Appropriate sizing | 2
Proxy sizing
| Correct calculations | 2
Size estimate
| E derived from db | 2
| Correct regression | 2
| Correct range | 2
Duration
| Correct productivity | 2
| Appropriate duration | 2
| Correct range | 2
Time in Phase
| Correct distribution | 2
Supporting Calcs
| Traceable if in error (max of -2) | 0
Base |  | 0
0
| Total | 20 | 0
Estimates on New Development: Please provide answers to the questions below. If a result is not calculable, please fill the box with a "NA" and defend your answer in the supporting calculations section. Each cell should contain a number, "NA", or a value from a drop-down menu; do not indicate units (such as "min", "hr", "LOC", etc.) Please do not leave any boxes blank; I will assume that an empty box means you did not answer the question.
Parameters
normal
log-normal
not applicable
LOCE x Time
LOCA x Time
Productivity
not applicable
VS
S
M
L
VL
not applicable
Calculation
Data
IO
Logic
Set-up
Text
not applicable
Object Category Sizes (in LOC/Method)
| Category | VS midpoint | S midpoint | M midpoint | L midpoint | VL midpoint | Method Used
| Calculation | 6.76 | 16.21 | 38.9 | 95.49 | 229.08 | log-normal
| Data | 10.71 | 15.135 | 21.379 | 30.2 | 42.65 | log-normal
| IO | 3.63 | 7.94 | 16.98 | 38.9 | 77.62 | log-normal
| Logic | NA | NA | NA | NA | NA | not applicable
| Set-up | NA | NA | NA | NA | NA | not applicable
| Text | NA | NA | NA | NA | NA | not applicable
Proxy Sizing
Object LOC (BA)
| Base Additions | Methods | Type | Size | LOC
| BA1 | 6 | Calculation | L | 852
| BA2 | 2 | IO | M | 25.25
New Objects (NO)
| New Objects | Methods | Type | Size | LOC
| NO0 | 5 | Data | VL | 196.6667
| NO1 | 2 | Data | M | 48.8
| NO2 | 4 | Data | L | 107
| NO3 | 3 | Data | M | 73.2
| NO4 | 5 | Calculation | S | 93
| NO5 | 7 | Calculation | L | 476
Size Estimate
| Base Additions (BA) | [5 empty] | 877.25 | LOC
| New Object LOC (NO) | [5 empty] | 994.6667 | LOC
| Estimated Object LOC (E) |  |  | E=BA+NO+M |  |  | 1885.9167 | LOC
| Regression Parm |  |  | B0 |  |  | 49.6294
| Regression Parm |  |  | B1 |  |  | 0.8519
| Estimated New and Changed LOC (N) |  |  | N=B0+B1*E |  |  | 1656 | LOC
| Estimated Total LOC (T) |  |  | T=N+B-D |  |  | 1997 | LOC
| 70% Prediction Range (Rangesize) |  |  | Rangesize |  |  | 317.4555 | LOC
| Upper Prediction Interval (UPIsize) |  |  | UPIsize=N+Rangesize |  |  | 1973.4555 | LOC
| Lower Prediction Interval (LPIsize) |  |  | LPIsize=N-Rangesize |  |  | 1338.5445 | LOC
Duration Estimate
| Productivity |  |  | Planned LOC/hour |  |  | 23.9195 | LOC/hour
| Estimated Project Duration (minutes) |  |  | method= | LOCE x Time |  | 4435 | Minutes
| 70% Prediction Range (Rangeduration) |  |  | Rangeduration |  |  | 144.3706 | Minutes
| Upper Prediction Interval (UPIduration) |  |  | UPIduration=Time+Rangeduration |  |  | 4579.3706 | Minutes
| Lower Prediction Interval (LPIduration) |  |  | LPIduration=Time-Rangeduration |  |  | 4290.6294 | Minutes
Time in Phase Estimate (minutes)
| Planning | 620.955 | Minutes
| Design | 931.433 | Minutes
| Code | 133.0619 | Minutes
| Compile | 133.0619 | Minutes
| Test | 2528.1767 | Minutes
| Postmortem | 88.7079 | Minutes
| Total | 4435.3978 | Minutes

## Calc-1
Supporting Calculations for "Object Category Sizes"

## Calc-2
Supporting Calculations for "Proxy Sizing"

## Calc-3
Supporting Calculations for "Size Estimate"
|  | x | y
| Identifier | Est. LOC (LOCe) | Actual LOC (LOCa) | Est. Duration (De) | Actual Duration (Da)
| Project1 | 124 | 98 | 360 | 300
| Project2 | 360 | 284 | 900 | 720
| Project3 | 229 | 292 | 540 | 720
| Project4 | 321 | 286 | 840 | 780
| Project5 | 279 | 350 | 720 | 900
| Project6 | 352 | 464 | 780 | 1380
| Project7 | 297 | 381 | 780 | 1020
| Project8 | 263 | 369 | 660 | 960
| Project9 | 357 | 365 | 900 | 900
| Project10 | 311 | 284 | 780 | 720
| Project11 | 341 | 277 | 840 | 600
| Project12 | 153 | 212 | 420 | 480
| Project13 | 390 | 319 | 1020 | 720
| Project14 | 260 | 218 | 660 | 540
| Project15 | 215 | 238 | 540 | 600
| Project16 | 468 | 312 | 1200 | 660
| Project17 | 528 | 676 | 1260 | 1620
| Project18 | 232 | 266 | 600 | 840
| Project19 | 304 | 225 | 780 | 600
| Project20 | 459 | 395 | 1080 | 1080

## Calc-4
Supporting Calculations for "Duration Estimate"
Range =
42 | 105
31 | 130
47 | 235
58 | 202
75 | 250

## Calc-5
Supporting Calculations for "Time in Phase Estimations"